Event Planner Guide

Guidelines for Alberta Council Provincial Level Events

PROVINCIAL COMMITTEE: ______________________________________________

PROVINCIAL ADVISER: _________________________________________________

Telephone: ______________	E-mail: _____________________________________

NAME OF EVENT: _____________________________________________________

DATE(S) OF EVENT: ___________________________________________________

FACILITY/LOCATION: __________________________________________________

Contact: _______________________Telephone ______________

**EVENT CO-ORDINATOR: _______________________________________

Telephone ______________ E-mail ________________________________________

PROVINCIAL OFFICE:	11055 – 107 Street NW, Edmonton, AB	T5H 2Z6

Telephone: 780-424-5510	Fax: 780-426-1715

REGISTRATIONS AND FINANCIAL:	  E-mail: accounts@albertagirlguides.com

NAMETAGS/HANDOUTS		  E-mail: data@albertagirlguides.com

**	Event co-ordinator is defined as the person(s) responsible for planning and carrying out the event.

Note:

- included in this packet are forms for the provincial committee adviser and event co-ordinator

- for events sponsored by camping, an additional form may be required from the camping adviser

Event Planner

Thank you for taking on the challenge of co-ordinating an Alberta Council provincial guiding event.

The content of this document is to assist with the details and planning for an event. The document is divided into guidelines for the provincial committee adviser and the event co-ordinator.

The most important consideration is that the success of the event relies upon a team effort. You are encouraged to create a team to assist you with the planning / co-ordinating of the event. It’s imperative the event co-ordinator and the provincial committee adviser have regular contact to ensure all facets of the event are considered.

If you find errors or omissions, or think of better methods or ideas, as you work through this document, please forward suggestions to the provincial committee adviser, requesting she share them with the appropriate standing committee adviser. These guidelines are to assist with the planning of events and, with your help, can be revised to ensure they are easy to use and appropriate for the events planned.

Once again, thank you for taking on this challenge.

Enjoy!

Guidelines for Alberta Council Provincial Events

Table of Contents

Provincial Committee Adviser	 (Event Planner)			Pages 3 and 4

Event Co-ordinator							Pages 5 to 9

Appendix 1	Information Sheet for Blue-Print, ANY_Guide News	Page 10

Appendix 2 	Safe Guide 						Page 11

Appendix 3 	Available from Provincial Office			Page 12

Appendix 4 	Participant Folder Suggestions, General		Page 13

Appendix 5 	After the Event - Guidelines for Event Report	Page 14

Appendix 6	Financial Statement (available electronically)	Page 15

Appendix 7	Printing Request Form (available electronically)	Page 16

Appendix 8	Event Merchandise and Crests			Page 17

Appendix 9	Government Grants					Page 18

# Event Planner — Provincial committee adviser (or member of committee responsible for event):

Comply with current edition of Safe Guide standards (Appendix 2). Ensure Guiders who lead events are members and have a current PRC and Safe Guide training.

____	Arrange dates and type of event one year to eighteen months in advance.

____	Determine general goal / theme for the event.

____	If the event is to be held at Alberta Guide House; complete booking forms (available from provincial office).

____	Get cost estimates (site rental, accommodation, meals, equipment rental, etc.).

____	Visit potential sites if necessary and arrange for provincial office to book facility. Ensure the event is added to the Alberta Council interactive calendar on the website.

____	Accommodation may be handled in one of two ways:

- make an all-inclusive booking: meals, sleeping, training rooms, etc.

- book training facility and some meals. Accommodation and breakfast is arranged by participants. Provide suggestions for hotels in the area, including costs.

____	Arrange to have contract written up.

____	Have contract signed by provincial contract signer. Arrange to have the cheque for the deposit produced (use an e-cheque requisition).

____	Select an event co-ordinator, in consultation with your committee.

____	Invite the Provincial Commissioner (or PC Team) to the event as soon as the date is set. Typically, the provincial adviser sends the invitation; advise the event co-ordinator this has been done.

____	Provide provincial office, in writing, the event details: name and date of event, location, cost, deadline date, and name, address and telephone number(s) of the event co-ordinator and who is authorized to approve expenses.

____	Invite provincial advisers (camping, cookie, international, membership, program, public relations and training) to provide input / ideas and involvement of their committees and members.

____	Send the following forms to the event co-ordinator:

- copy of the budget for the event

- provincial newsletter deadlines

- copy of notification to provincial office giving financial authority for the event

- e-cheque requisition form

- event financial report and worksheets

- expense account forms (available from provincial office)

- previous event evaluations, budgets, participant letters / information, program and reports including the final financial report

- Event summary page - this needs to be filled out and sent to the provincial office as soon as possible and registrations are unable to be taken unless this is done

____	Act as liaison between all parties involved in the event. Review the guidelines in detail with the event co-ordinator to ensure they know what is expected.

____	Using the budget, and in conjunction with the event co-ordinator, set a registration fee for participants for the event, to cover accommodation, meals, photocopying, supplies, program or trainer expenses and, if necessary, facility rentals.

____	Determine if event qualifies for a government grant (Appendix 9) and determine who will complete the application process.

____	Keep in regular contact with event co-ordinator to monitor progress.

____	Send event information, schedules, programs and accommodation, etc. to the Provincial Commissioner (or PC Team) and other invited guests who the event co-ordinator has confirmed are attending.

____	Invitations for out-of-province participants must be submitted by March 15th of the year prior to the event and are send by the Provincial Commissioner.

____	After the event, file a copy of the event financial report to the provincial office or the applicable provincial adviser.

Provincial Event Information Summary

Alberta Council

Name of Event: ___________________________________________________

Date(s) of Event: __________________________________________________

Event Location:  __________________________________________________

Committee Responsible for Event: ____________________________________

Responsible Guider(s):______________________________________________

Maximum number of participants: _____________________________________

Maximum number of wait list participants (if applicable): ____________________

Cost of Event (not including GST): ____________________________________

Please list all pricing and/or accommodation options (use back if necessary)

________________________________________________________________

________________________________________________________________

Deadline for Registration: ___________________________________________

Please provide a list with the names of Guider(s) paid fully through the event, and, the names of Guider(s) paid partially through the event and cost to that participant:

________________________________________________________________

Most events will be available for online registration. For those who may require a paper registration, please attach the Provincial Event Registration Form for this event (title and event date are the only things that should be altered) and any additional registration questions or information that needs to go with this on a second page.

Please submit to the Accounting Clerk at the Alberta Council office, and they will see to the event being prepared for registration and posted on the website, and coordinate the opening of registration with the event organizers.

Please be aware that it takes a few days to have all the elements prepared and coordinated before registration is declared “open” and therefore please plan to get all needed information to the office a few days before your desired “open” date.

Event Co-ordinator

You need a team!

Event Co-ordinators are responsible for finding a team to handle the program / activities as well as the comforts of participants and trainers / presenters throughout the event. This team includes the trainers / presenters and those who provide support for the participants’ needs (meals, accommodation, supplies, etc.). A central table should have a first aid kit available, emergency contacts, schedule, facility maps, registration forms (for the participants), and information about where to find what during the event.

____	Choose your team members. Contact the Provincial Training Adviser for information regarding Trainers’ interests and experience in modules to assist you with selecting a well-rounded team.

____	Submit event announcement / teaser ad to the Blue-Print editor and website

(four to six months before event). Submissions must go through the provincial committee adviser, and will be approved by the office before being posted to the website.

____	The event co-ordinator is responsible for the finances although she may delegate the duties of record keeping.

____	In consultation with the provincial adviser, contact the facility as soon as possible for the number and type of break-out / meeting rooms required.

____	The budget should include shared accommodation for all team members. Very few single rooms will be available upon request and at the cost of the participant.

____	Review the budget to determine registration fee and / or costs required, in conjunction with committee adviser. Remember to include participants’ accommodation, meals, session rooms, facility rentals, out trips, trainers / presenters and guest costs, etc. Set registration fee in consultation with provincial adviser.

____	Please consult the Alberta Council cancellation policy on form AB-Council.07. and consider travel parameters.

____	Inform provincial adviser of suggestions for resource people / guests to be invited; forward invitation to people selected (keep finances in mind). If a gift or honorarium is to be given, ensure it will be forwarded promptly. Any fee is usually paid upon receipt of invoice. Honorariums are usually presented at the event.

____	Determine additional trainers / session presenters needed for specific session topics and invite them to train at the event.

____	Prepare the information sheet (Appendix 1) for the Blue-Print editor, ANY_GuideNews editor and webmaster. Submit to provincial committee adviser. Note: Ensure you meet deadline for newsletter issue that will be received at least one month prior to event deadline.

____	Alberta Council now encourages the use of online event registration. Send the information for your event, including pricing structures and participant options to the Accounts Clerk so that the new registration module can be set up.  For those participants who need/wish to use paper registration, the event registration form (AB.Council.07) can be used. Other than adding an event title and date, organizers are not to alter this form, however, you can create a second form to be used with it that would include more questions specific to your event, and information you wish to share.

____	Event information and session choices can be posted on the Alberta Council website along with the link to online event registration and contact information for registration assistance. This information is to be sent first to the Alberta Council office (accounts@albertagirlguides.com), and they will coordinate the launch of online registration with event organizers and the webmaster.

____	Send event information, schedules, programs and accommodation, etc. to the provincial adviser who will forward to the Provincial Commissioner (or PC Team) and other invited guests. Ensure they are registered as participants.

____	If funds are needed to cover expenses, you can request an accountable advance from the provincial office - e-mail accounts@albertagirlguides.com to acquire the appropriate form. Advance cheques will include a form showing breakdown of expenses. This form (with receipts) must be returned with the balance of the money or a request for additional funds. Include this information in the event financial report.

____	Check with your team to see which of the following are needed: equipment, supplies, room size, room set-up required, etc.

____	Create logo for event – provincial office may assist, with plenty of lead time. Be sure to share this responsibility with other event team members. Design must be approved by deputy provincial commissioner responsible for approval of crests and merchandise (form AB-PR.01).

____	Logo can be used to create a crest or merchandise for the event with the approval of the deputy provincial commissioner - the approval form must be submitted a minimum of two weeks prior to ordering (Appendix 8).

____	Prepare an evaluation form for the over-all event (to include evaluation of accommodation, training facility and catering, etc.)

____	Prepare session evaluation forms, and ensure they are distributed to the trainers / presenters of individual sessions, if applicable.

____	Advise provincial office regarding services and items they will be providing for the event (participant list, session choices, registration folders, buttons, name tags and holders) (Appendix 3).

____	Book provincial office equipment required by trainers / presenters (laptop, LCD projector, flip charts, etc.) well ahead of time. Finalize audio-visual contract with facility (if required).

____	Pay bills promptly and keep an accurate record of all financial transactions. Keep all receipts.

____	With your team, decide who is responsible for opening and closing ceremonies, reflections, Guides’ Own, graces, crafts and introduction of team members.

____	Inform team members of accommodation and travel arrangements. Determine if the team will provide their own transportation or if alternative arrangements need to be arranged (i.e., transportation to and from bus depot or airport to the facility).

____	Where online registration is not used, forms and fees are to be forwarded directly to the provincial office for processing of payments. The office will use iMIS meeting module to create a participant list, name tags, etc.

____	Finalize the transportation / accommodation for your team and guests.

____	Provide the provincial adviser (or her designate) with regular status reports during the planning stages of the event. Send copies of all correspondence to provincial adviser.

____	Send to the provincial adviser (or her designate)

- copy of the final program

- name of trainer / program deliverer and number registered for each session

- session evaluations

____	Arrange for the printing of the final program by provincial office. Briefly and clearly describe the content of each session and, if possible, who is facilitating that session. Send copies to all members of the training team in advance. (Appendix 7) You need to have all printing to the provincial office a minimum of 2 weeks in advance.

____	Determine a deadline for trainers to submit print / photocopy requests. Printing projects should be submitted to the office complete from the co-ordinator, not in pieces from various contributors. Submitting printing requests three weeks ahead is preferred - two weeks minimum prior to event. If material is being picked up, advise office when, who, etc. Send the office a copy of the print request form (Appendix 7). Note: form is available electronically from the provincial adviser.

____	Send participant folder contents (Appendix 4) to provincial office for printing and assembling — the folders will be assembled by the office, but the contents must be determined by the team (Appendix 7).

____	Obtain a supply of Health Forms (H.2) from provincial office to have at registration desk for participants who did not bring one with them.

____	Obtain a supply of expense forms from provincial office and distribute to team members for mileage and session expenses.

____	Prepare an information package for participants; send via e-mail, if possible. The letter should include: time event begins and ends, kit list, session topics and outline, map to facility and accommodation, emergency telephone number and uniform requirements. Information regarding music books, publications, etc. to be used would be helpful. Include a telephone number participants can call if they are going to be late or are unable to attend at last minute. The information should request a Health Form H.2 be completed and brought to training (participants should keep the Health Form on their person). Include program session choices, if possible.

____	Send out acknowledgement of registration form / fee with information package — e-mail if possible.

____	Request provincial office to send registration report to you on a weekly basis. Office staff are willing to work with you wherever possible as to your information needs.

____	Adhere to deadline set. Deadline dates are firm as per provincial policy.

____	Request a participant list after the deadline.

____	Assign training rooms to trainers / topics based on session registration.

____	Make directional and / or room identification signs. You may also wish to make a large wall copy of the program.  Please note the requirements of the facility with regards to putting paper on the walls.

____	Provide a suitable first aid kit to be kept at the registration desk.

____	Set menu with caterer for food and beverages (consider allergies and dietary requirements of participants). For facilities that set their own menu, ensure you send the allergy / dietary requirements as soon as possible after the deadline.

____	Ensure a cloakroom or coat rack is made available, if possible.

____	Confirm transportation schedules: airlines, buses, cars, if applicable.

____	Confirm facility accommodations.

____	Prepare transportation and accommodation schedules (include arrival time, flight number, airline, person assigned to meet flight), if applicable.

____	Organize staffing of the registration desks to avoid line-ups. Registration desk personnel should be on duty at least one hour prior to event starting time.

____	Final walk-through with team (if possible).

____	Have helpers on duty at the training to: assist trainers / program deliverers with luggage, supplies, etc., move chairs and tables, set-up equipment, operate lost and found, clear up after training, if needed.  Please keep the budget in mind with this.

____	During the event be aware of the program deliverers’ / trainers’ personal needs (if time is short, make sure refreshments are taken to their training rooms).

____	After the event — send the iMIS generated participant list to provincial office for activities / trainings (TEAM modules) attended as this is entered into iMIS records.

____	Send reminder e-mails to the program delivers / trainers about submitting their expenses — aim to have all expense requests in by the end of the event.

____	Submit all expense accounts to the provincial office within four weeks of the event. All such submissions must have a verifying signature on them; the provincial adviser should sign the expense form for the event co-ordinator.

____	Complete the event financial report (Appendix 6) within six weeks of the event and forward a copy to the provincial adviser and deputy provincial commissioner. Retain one copy for yourself as follow-up.

____	Send an event evaluation and report (Appendix 5) to the provincial adviser (or her designate) within six weeks of the event. This report should include the following information from the over-all evaluations: general atmosphere of training, suitability of facilities, any problems encountered by the team, suggestions for future events / trainings, anything else you consider important.

# Appendix 1

Information Sheet for Blue-Print to Include:

- Event Information

- name of event

- date, place and time event begins and ends

- address and telephone number of both event facility and accommodation

- Program information

- who the event / training is for (Ranger Guider, commissioner, etc.)

- general program outline or session descriptions (including additional costs for particular sessions, i.e. $10 for booklet, etc.)

- any prerequisites

- Financial Arrangements

- full cost and what it covers.

- refund policy (is fee non-refundable or transferable after a certain date? Please consult Alberta Council cancellation policy on form AB-Council.07.

Note: any participant who assumes the transferred registration of another participant will also assume the program and room assignments and their name will not appear on the participant list.

- cancellation information

- registration fee must accompany application or credit card number, expiry date and signature

- include this statement “it is the participant’s responsibility to ensure that application forms and fees arrive before the deadline. The participant will not be processed or registered until both the registration form and the payment have been received.”

- Advise if there is a limited number of registrations accepted (if there is a limit); registrations received after the limit will be notified the event is full.

- Deadline for registration to be received by provincial office — emphasize the date.

- Where to register online, and office contact number (780-424-5510) if you need assistance or paper registration. If registering by paper, send form and fee to provincial office. Note: Cheques are payable to Girl Guides of Canada, Alberta Council

- Accommodation and meals (be very clear about hotel reservations, and where to send money, etc.).

Use ANY_GuideNews to put a “teaser” that links or directs Guiders to the
Alberta Council website for more detailed information.

Appendix 2

Safe Guide

The current issue of Safe Guide is available at www.girlguides.ca under Guider Resources. More information can be obtained by contacting assessor@albertagirlguides.com.

Guiders are expected to apply the same principles of thorough forethought and safe planning in all Guiding-related activities, whether they are for girls or adults.

Adult only activities, except for meetings and conferences, must comply with points listed in Appendix A of the current Safe Guide.

All Yellow and Red level activities and international travel must be assessed by a Safe Guide Assessor before they can proceed. Ensure an appropriate amount of time is allowed for the assessment of these activities.

For staffing events consult the Supervisors section in the current Safe Guide.

Consult Alberta Council’s Best Practices for Large and Multi-Unit Events for more information.

Any questions can be directed to assessor@albertagirlguides.com.

Updated:  May 2014

# Appendix 3

Services Provided through the Provincial Office:

Online registration, or, paper applications and cheques for events are received by the provincial office:

- receipts issued for cheques

- listing of participants available whenever needed

- listing of other information as needed — dietary, allergies, travel, accommodations, sessions

iMIS Meeting Management Module

- Attendance and activities are added to participant’s iMIS record after the event. This is entered from the sign-in sheets provided by the office, which must be returned for entry. Hand-made sign-in sheets will not be accepted.

Equipment available through the office:

•	flip charts (5), portable display boards (2), portable screen, laptops (2), LCD projectors (2).

See Appendix 7 for:

- printing of all handouts

- nametags holders (with or without names) for participants

- labels with participants’ names (for folders)

- labels with participants’ names and addresses for mail outs (if not done out of provincial office)

- folders

Office staff do have a list of caterers but do not book the caterers (must be done by event co-ordinator).

Printing Fees for most commonly requested …

| White paper | 8 x 11 / paper & one sided copy | $0.03 |
| --- | --- | --- |
| Colored paper | 8 x 11 / paper & one sided copy | $0.04 |
| White paper | 8 x 11 / paper & double sided copy | $0.05 |
| Colored paper | 8 x 11 / paper & one sided copy | $0.06 |
| Color copies | 8 x 11 / white paper & one sided | $0.13 |
| Color copies | 8 x 11 / white paper & double sided | $0.25 |
| Labels | Works out to 0.30 & 0.50 per sheet, depending on size | $0.02 per label |
| Name tags | Holder, string & insert | $0.65 |

(please contact the office for costs of other items)

Appendix 4

Participant folder suggestions: (Sticker with the logo and participant name label on front of the folder)

- welcome note to participants including housekeeping information — who to look to for help, where to find whatever they are looking for

- schedule / program

- orientation to site / location information (map of facility)

- participant list

- session evaluations (one per session)

- evaluation for the weekend

- blank paper for notes

General:

- leave yourself enough time to plan well — effectively, efficiently and thoroughly

- decorations re theme — walls, tables, doors, hallways, entrances, foyers, session rooms, participant rooms, meeting rooms, dining rooms, washrooms

- flowers, posters, balloons, streamers, etc.

- table favours

- give-aways and take-aways — gifts, promotional items, crests, bookmarks, magnets (with logo), pins (only one item and one crest per event is permitted and permission must be obtained from the deputy provincial commissioner)

- door prizes

- Canadian World Friendship fund activity — door prizes (sell tickets), raffle, auctions

- activities for times between sessions or during free time

- at the event

- introduce members of Alberta Council, provincial advisers and members of her committee, area commissioners, guests and team members

- thank your volunteers (appreciation to team members and others) tangible (card, crest).

- Thank special guest(s).

Appendix 5

After the Event — Guidelines for Event Report

The feedback you receive and what you experienced during your planning sessions is valuable information. Please ensure you can provide as much detail as possible in the report to assist with future planning. Collation of the evaluation would be particularly helpful to the adviser.

Opening Section:

- Goals for the event (personal, area, other, etc.).

- Overall impressions at beginning of the event.

Training Section:

  - Overview of what was offered (include timeframes, breaks between, different streams covered, enrichment sessions, other sessions, etc.).

  - Feedback of selections, topics, etc., as well as number of participants in sessions and of trainers involved.

  - What worked, what didn’t work?

  - Things that should have happened, but didn’t (for whatever reason).

  - Suggestions for next year.

Overall Event/Facility Section:

    - Advertising and pre-event items (team organizing, planning, etc.) — was there enough, donations received, community support, etc.

    - Review of facility.

    - Feedback about facility, food, accommodations, etc. including value received, problems, etc.

    - Items included in the participant / trainer folders.

    - General overview of agenda/program.

    - What was done for theme, how theme was carried through.

    - What worked, what didn’t?

    - Things that should have happened, but didn’t (for whatever reason).

    - Suggestions for next event.

Closing Section:

      - Were the goals met?

      - Overall impressions and feelings about the event.

# Appendix 6

GIRL GUIDES OF CANADA-ALBERTA COUNCIL

FINANCIAL STATEMENT

For Provincially Approved / Sponsored Events

- attach to the report submitted to the sponsoring committee

- attach the SG.3 form (if girls were present at the event)

- submit this form within six weeks after the event

Event: 	 Event Dates:

Location:

Name:

Person filling out the Financial Statement

Income

Event/Camp Fees: (Fee $_____ x ____# of participants)	$ __________

Donations	$ __________

Other (specify)

______________________________________	$ __________

______________________________________	$ __________

Total Income		$ __________

Expenses

Site rental fee	$ __________

Food	$ __________

Transportation	$ __________

Program: (crafts, special activities etc.)	$ __________

Crests	$ __________

Equipment and supplies	$ __________

Administration: (telephone, photocopies etc.)	$ __________

_________________________________	$ __________

_________________________________	$ __________

_________________________________	$ __________

Total Expenses	$ __________

Balance		$ __________

That the refund policy for provincially sponsored and approved events will be refunded for not less than 15% of the cost of the event and cheques will not be issued for less than $25.00. C11.10.19

Signature of Responsible Guider:

iMIS #: 	 Date:

Appendix 7

PRINTING REQUEST FORM

Date requested: ____________________	Final date required: ________________

Charge to: ________________________	Requested by: ____________________

Approved by: __________________________

Required by: _________________	Event: __________________________

Item_________________________________________________________Quantity: _______________________

Main paper colour: ________ 	
 requires a different coloured front cover -	__________

 requires a coloured back cover -	   	__________ 
 single sided	 double sided 	 three hole punched		  stapled

 Other special instructions:

────────────────────────────────────────────Specialty Items

 Labels		  Name Tag Holders 	 Folders	 Other________________

────────────────────────────────────────────

Envelopes:

 #10 Standard 	 5 ½ X 8 	 9 X 12 	 10 x 13 	window 	 other

────────────────────────────────────────────

Postage or Shipping:

 For pick up by: ______________________________________________________________

 Mail to: ____________________________________________________________________

 Ship by courier to: ___________________________________________________________

Charge Courier to Acct #

For Office Use Only 
Date completed: _____________________________________________________

Date mailed or picked up: _________________________________________________

Signature of person authorized to pick up

Order # _______________________________	Invoice #_________________________

(See page 13 of this Event Planner Guide for pricing of common items)

Appendix 8

Event Merchandise

One item per event may be produced. Event merchandise may be developed by event organizers and may be clothing: t-shirt, sweater, hat; or other product: binder, bag, or pen. This does not include variations of that item (e.g. t-shirt with long sleeves or t-shirt with short sleeves, not both). The merchandise must include the name and date of the event and may include the event’s theme / logo or other information. Event merchandise must include the GGC logo as specified in the Graphic Standards Manual in Member Zone – Policies and Procedures – Graphic Standards.

Crests

You may produce one event crest in addition to the one item of merchandise per event.

The information regarding a crest is to be submitted to the provincial deputy commissioner using form AB-PR.01–Crest / Logo Use Approval (found on our website under public relations at www.albertagirlguides.ca/forms). Please note the form must be submitted a minimum of two weeks before ordering the crest.

Appendix 9

Government Grants

All grant applications for provincially sponsored / approved events must be approved by the Alberta Council Executive Committee prior to forwarding applications to the appropriate government body. (March 2011)

In addition:

All applications for government grants above the municipal level must be submitted through the provincial fund development co-ordinator.

The following must be included:

- FR. 1

- grant application fully completed with original signatures

- all necessary attachments as required

- grant summary sheet (AB.04) with area commissioner’s signature

- copy of the minutes from area council approving application

If applying for a travel grant under the Community Investment Program (CIP) grant, the current maximum request allowed is $10,000 or $1,000 per GGC member traveling up to $10,000, whichever is less.

All government grant applications should be delivered to the provincial office at least two weeks prior to the grant application deadline to allow processing time.

The provincial fund development co-ordinator is available to assist with grant applications and should be contacted early in the process as some projects/grants may require additional time for approvals.

Retroactive grant applications for monies already spent are not usually accepted by government, so plan and apply early.